## Sheet1
Date	topics	status
18/12/17	Added 10 questions in sourabh faculty panel of maths	passed
	tried to add scroll bar to the question list	failed
	set two quiz	passed
	tried using varchar(20) , 100 pattern for date	failed
	use order by caluse for the query	passed
	merge two query into one to get quiz details	passed

	http://www.cfwebstore.com/index.cfm/blog/161/failed-to-set-cookie-in-cf1011.cfm	passed
	https://www.bennadel.com/blog/1131-ask-ben-ending-coldfusion-session-when-user-closes-browser.htm	passed		35mins

	created getQuizQuestions.cfc	done
	written query to get the quizquestions	done		25mins

	discussion with himansu about the session issue			40mins

	discussion with asish		01:15:00 PM	02:00:00 PM
	discussion with asish to resolve the prob	successful	03:00:00 PM	05:00:00 PM
	making the changes accordingly in my application and testing it in diff browsers
	enabling the dibugger and changing the bindings			06:00:00 PM

	adding radio buttons and modifing the testStart.cfm			06:20:00 PM
	addjusting the table where the question is displayed to the students			06:40:00 PM
	reading about how to keep a page active only for a specific time		06:45:00 PM	07:05:00 PM
	set serial number the the loop of query using cfoutput			07:15:00 PM

19/12/17	experiment with server time and display of test page		11:10:00 AM	12:10:00 PM

	studing about cfschedule			12:50:00 PM
	Study and experiment with JS “settimeout”			01:30:00 PM
	raise the iwin for ecllipse		03:15:00 PM
	discussion with Durga and installation of ecllipse		03:40:00 PM

20/12/17
			10:30:00 AM	11:30:00 AM
21/12/17	complete the js code for dynamic button
	downlaod git and git desktop
	learn commands
	upload files in git			01:30:00 PM

25/12/17	email server setup		11:30:00 AM
	try and test the email send and receive			12:30:00 PM
	create testValidationService.cfc			01:30:00 PM
	work on testSubmit.cfc and testValidation.cfc		02:30:00 PM	04:30:00 PM
	discussion with asish about the calculation of results of users in demo project: / 1. discussion on table “quiz”, “questions”, “quizQuestion”,”score” / 2. have been asked to store score of each user for perticular quiz / 3. asked to remove “quizQuestionId” from “quizQuestion” table / 4. and if the requirement asks then append the questions and answers in a column with append string. / Demo of score table: / 1. scr id, / 2. exam id, / 3. user id, / 4. attemptedquestiondetail,1. qid, 2. correct ans, 3. user ans, 4. status / 5. user score (in percentage)		05:00:00 PM	05:30:00 PM

	created onTestSubmit			06:30:00 PM	including break
	learn about query of query and endocing for cross site scripting
	modified the score table in db.