## Sheet1
Admin Module:- Faculties page and Student page:-

1. Separate the view of list of faculties and students.
2. Add data-tables in the view,
3. Add search , sorting and pagination using the server side processing.
4. Add edit, modify, delete functionality for the tables
5. Remove the bug : “Server side validation error message is not being shown when JS is disabled and the page gets reloaded.”
	13hours
Faculty Module:-

1. Add data-tables in every view section,
2. Add sorting, searching , pagination in all the view sections.
3. Add filter by single as well as multiple quiz to view results for the students for the corresponding quiz.
4. Add export functionality to view the results of all the students for all the quiz set by that particular faculty.
5. Add export functionality to view the results of all the students for the particular quiz set by that particular faculty as well as for the number of filtered quiz.
6. Make the score of a student clickable where the modal will display the questions with user answers and correct answers
7. Add export functionality for view of students performance.
8. Functionality to remove and add questions for the upcoming selected quiz.
9. Functionality to edit, delete the questions in question bank only for the question which didnt appear in any of the quiz.
10. Add export functionality for the quiz questions set by the faculty.
	26hours
Students Module:-

1. Students will be able to export their performance report for all the quiz they have appeared .
2. Implement data-tables for viewing the performance report.
3. Add search, delete, sorting functionality int the view of performance report.	5-6 hours

application:

1. Use of session rotation.
2. Functionality of recovering new password for forgotten password.
3. Using no-script everywhere in the application.	4-5 hours

testing the application after all the functionalities has been added	3hours

After the estimation I will submit the application on 20th of February 2018.